## Readme (Definitions)
Definitions
Scope Assessment (By Business Team)
Unit Dimension | 1 - Small (1-3) | 3 - Medium (4-6) | 5 - Large (>6) | Complexity Index | Example
User interactions | 1 - 3 count of user interactions | 4 - 6 count of user interactions | >6 count of user interactions | 4 | -Entry point -Save as draft -Submit -Cancel -Withdraw -Concurrent user check
No. of pages | 1 - 3 count of no. of pages | 4-6 count of no. of pages | >6 count of no. of pages | 2 | -Steppers -Module dashboard
No. of integration with external parties | 1 - 3 count of no. of integration | 4-6 count of no. of integration | >6 count of no. of integration | 8 | -View status of the due diligence reports -Download the due diligence reports
Reusability Assessment (By IT Team)
Reusability dimension | 0 - No reusability | 1 - Low reusability | 2 - Moderate reusability | 4 - High reusability
Screen (Frontend) | All screens need to be built from scratch | Limited screens/components can be adapted | Some screens/components can be adapted | Most screens/components can be reused as-is
Business logic (Backend) | Logic needs to be fully redesigned | Limited logic can be adapted with modifications | Some logic can be adapted with modifications | Minor tweaks on existing logic
Interface | New integration endpoints to be established | Limites rework on existing integration endpoints | Some rework on existing integration endpoints | Most of the existing integration endpoints can be reused
Database | > New Schema & New Set of Tables along with Supporting Objects (View, Audit & Triggers) | > New Table along with Supporting Objects (View, Audit & Triggers) | > Addition/Removal of Columns in Table & Views. > RLS Policy Changes | > Master Data & Notification Template changes.
QA | All test cases/scripts need to be written from scratch | Limited test cases/scripts can be adapted | Some test cases/scripts can be adapted | Most test cases/scripts can be reused or regression-run
Reusability % |  | Adjustment %
0 | 24 | 0%
25 | 50 | -35%
51 | 74 | -65%
75 | 100 | -85%
Note:
1. Smallest reusability % is 25% (With only 1 dimension with low reusability, other dimension not applicable)
2. Adjustment % populated based on median of reusablity % range, round to nearest 5%

## MasterData
Name | Value
User Interaction (S -1, M- 3 & L -5) | 4 | * Complexity index
Pages (S -1, M- 3 & L -5) | 2 | * Complexity index
Integration (S -1, M- 3 & L -5) | 8 | * Complexity index
Reusability Score (0 -24) | 0%
Reusability Score (25 - 49) | 35%
Reusability Score (50 - 74) | 65%
Reusability Score (75 - 100) | 85%
Requirement & Design | 20%
Tender Story Point | 1.16 | *Based on past CRs
QA (% of Development) | 40% | *Summary sheet
Req. & Design (% of Development) | 20% | *Summary sheet

## Tender Story Points
S/No | Epic | US # | US Summary | Scope Assessment (By Business Team) | [6 empty] | Reusability Assessment (By IT Team) | [9 empty] | Reusability Score | Adjustment % | Framework Unit (Aft. Adj.) | Req. & Design Unit | TSP
|  |  |  | User Interaction | User Interaction Details | Pages | Page Details | Integration | Integration Details | Framework Unit | Frontend | Frontend Details | Backend | Backend Details | Interface | Interface Details | Database | Database Details | QA | QA Details

## Details
S. No | User Story | Business Requirement | Technical Component(s) | UI |  |  | MS |  |  | DB |  |  | BPM |  |  | DEV Efforts (MD)
|  |  |  | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex

## Summary
Activity | Total | Original Efforts
Development
QA
Requirement & Design (Story ideation, UI design, Technical design)
Total